## Task Breakdown
Task ID | Phase | Epic | Workstream | Task Name | Description | Deliverable | Depends On | Source Section | Priority | Suggested Owner | Status | Acceptance Criteria | Comments | Last Updated
E-001 | Phase 0 | Architecture Planning | Program Setup | Validate scope and success criteria | Review the target architecture end to end and define success criteria for shared email ingestion, routing, outbound messaging, and governed automation across AP and procurement. | Approved scope statement and success metrics | None | 1. Architecture goal; 21. Final architecture summary | Critical | Product + Architecture | Not Started | Success metrics cover inbound, outbound, routing accuracy, governance, and tenant isolation.
E-002 | Phase 0 | Architecture Planning | Decision Management | Confirm target-state architecture decisions | Convert the six target-state decisions into an implementation baseline and secure sign-off for one shared app, deterministic-first routing, scoped agent tools, and separate downstream domain execution models. | Decision log and sign-off record | E-001 | 20. Recommended target-state decisions | Critical | Architecture Review Board | Not Started | Each target-state decision is approved, versioned, and referenced by implementation workstreams.
E-003 | Phase 0 | Architecture Planning | Delivery Planning | Create implementation roadmap and sprint plan | Break the delivery into implementation waves, align teams, and map dependencies across models, services, handlers, APIs, UI, security, and testing. | Roadmap with milestones and sprint sequencing | E-001, E-002 | 19. Recommended implementation phases | High | Program Management | Not Started | Roadmap shows phase entry and exit criteria plus team ownership.
E-004 | Phase 0 | Architecture Planning | Provider Strategy | Define mailbox rollout strategy | Decide which tenant mailboxes, providers, and environments are in scope for pilot, staged rollout, fallback polling, and recovery sync. | Mailbox rollout matrix | E-002 | 9. Provider integration design | High | Platform Operations | Not Started | Pilot scope, production scope, and provider priorities are documented.
E-005 | Phase 0 | Architecture Planning | Non-Functional Design | Define SLAs and operational guardrails | Set target SLAs for ingestion latency, outbound delivery, retry windows, attachment processing, sync health, and mailbox recovery. | Operational SLA and guardrail document | E-001 | 15. Security, RBAC, and governance; 19. Recommended implementation phases | High | Platform Architecture | Not Started | SLA values and breach handling rules are agreed and measurable.
E-006 | Phase 0 | Architecture Planning | Governance Design | Define tenant, retention, and data residency approach | Specify tenant scoping, retention policies, mailbox credential boundaries, blob retention, and email artifact lifecycle rules. | Governance and retention design note | E-001 | 15. Security, RBAC, and governance | High | Security + Compliance | Not Started | Retention, residency, and mailbox credential rules are documented for each artifact type.
E-007 | Phase 0 | Architecture Planning | Cutover Planning | Define cutover and backfill approach | Plan how the platform will move from no shared email layer to controlled go-live, including historical backfill, replay, and issue containment. | Cutover and backfill runbook | E-003, E-004 | 9. Provider integration design; 19. Recommended implementation phases | Medium | Platform Operations | Not Started | Runbook covers initial sync, replay logic, rollback, and incident response.
E-101 | Phase 1 | Shared Email Foundation | App Scaffold | Create apps.email_integration structure | Scaffold the new app with admin, models, urls, views, api, services, domain_handlers, tools, tasks, signals, enums, and migrations folders aligned to the architecture document. | New email integration app structure committed | E-002 | 3. New app structure | Critical | Backend Platform | Completed | App structure matches the target design and is wired into project settings and URLs. | Verified existing apps.email_integration scaffold with app, services, domain_handlers, tools, tasks, views, API, migrations, and templates. | 2026-04-23
E-102 | Phase 1 | Shared Email Foundation | Configuration | Register app configuration and extension points | Add settings, URL registration, feature flags, queue names, and provider configuration placeholders needed to enable email integration safely. | Project configuration changes for email integration | E-101 | 2. Target high-level architecture; 3. New app structure | Critical | Backend Platform | Completed | Email app can be enabled per environment without breaking existing flows. | Verified email integration app registration, mounted UI/API routes, and settings entry for webhook shared secret. | 2026-04-23
E-103 | Phase 1 | Shared Email Foundation | Enums | Add canonical email enums | Implement shared enums covering message classification, processing status, sender trust, email intent, message direction, routing status, and action types. | Email enums in the correct enum location | E-101 | 5. Important enum design | Critical | Backend Platform | Completed | Enum set fully covers the document taxonomy and matches usage across models and services. | Verified shared email enums implemented in apps/email_integration/enums.py for provider, routing, trust, actions, and processing states. | 2026-04-23
E-104 | Phase 1 | Shared Email Foundation | Data Model | Implement MailboxConfig model | Create the tenant-scoped mailbox configuration model with provider, auth, routing defaults, sync health, webhook or polling settings, allowed sender domains, and active status. | MailboxConfig model, migration, and admin registration | E-103 | 4. Data model design | Critical | Backend Platform | Completed | MailboxConfig supports tenant scope, provider metadata, health state, and safe activation. | Verified MailboxConfig model, migration, and admin registration already exist. | 2026-04-23
E-105 | Phase 1 | Shared Email Foundation | Data Model | Implement EmailThread model | Create the canonical conversation model to store normalized subject, provider thread identifiers, timestamps, domain context, and nullable business links. | EmailThread model, migration, and admin registration | E-103 | 4. Data model design | Critical | Backend Platform | Completed | EmailThread can link to AP and procurement entities while keeping thread-level metadata. | Verified EmailThread model and migration already exist. | 2026-04-23
E-106 | Phase 1 | Shared Email Foundation | Data Model | Implement EmailMessage model | Create the canonical inbound and outbound message model with headers, body variants, classification, trust, routing status, trace fields, provider payload, and entity links. | EmailMessage model, migration, and admin registration | E-103 | 4. Data model design | Critical | Backend Platform | Completed | EmailMessage stores normalized content, provider identifiers, and domain processing state. | Verified EmailMessage canonical model and migration already exist. | 2026-04-23
E-107 | Phase 1 | Shared Email Foundation | Data Model | Implement EmailAttachment model | Create attachment tracking with content metadata, hash, blob path, scan status, classification, linked DocumentUpload, and processing status. | EmailAttachment model, migration, and admin registration | E-103 | 4. Data model design | Critical | Backend Platform | Completed | Attachments can be independently scanned, deduplicated, and linked to uploads. | Verified EmailAttachment model and migration already exist. | 2026-04-23
E-108 | Phase 1 | Shared Email Foundation | Data Model | Implement EmailParticipant model | Create optional participant storage for analytics, role typing, trust scoring, and linked vendor or internal user context. | EmailParticipant model, migration, and admin registration | E-103 | 4. Data model design | High | Backend Platform | Completed | Participants can be joined to messages and support trust analytics. | Verified EmailParticipant model and migration already exist. | 2026-04-23
E-109 | Phase 1 | Shared Email Foundation | Data Model | Implement EmailRoutingDecision model | Persist routing outcomes, evidence, confidence, deterministic or LLM path, rule version, final handler, and execution status for every processed message. | EmailRoutingDecision model, migration, and admin registration | E-103 | 4. Data model design; 6. Domain routing architecture | Critical | Backend Platform | Completed | Every routed message has a durable decision record with enough evidence for audit and replay. | Verified EmailRoutingDecision model and persistence flow already exist. | 2026-04-23
E-110 | Phase 1 | Shared Email Foundation | Data Model | Implement EmailAction model | Create the action ledger for all email-triggered mutations, including actor, payload, result, trace ID, and error context. | EmailAction model, migration, and admin registration | E-103 | 4. Data model design; 15. Security, RBAC, and governance | Critical | Backend Platform | Completed | Every email mutation can be reconstructed from EmailAction records. | Verified EmailAction audit ledger model and persistence flow already exist. | 2026-04-23
E-111 | Phase 1 | Shared Email Foundation | Data Model | Implement EmailTemplate model | Create reusable outbound template storage with domain scope, subject and body templates, approval requirements, variables, and active state. | EmailTemplate model, migration, and admin registration | E-103 | 4. Data model design; 17. UI design | High | Backend Platform | Completed | Templates support safe variable substitution, approval metadata, and active versioning. | Verified EmailTemplate model, migration, and admin registration already exist. | 2026-04-23
E-112 | Phase 1 | Shared Email Foundation | Migrations and Seeds | Create migrations and seed baseline records | Generate migrations, default statuses, default action types, queue names, and any baseline template categories or mailbox settings. | Migration set and optional seed command updates | E-104, E-105, E-106, E-107, E-108, E-109, E-110, E-111 | 3. New app structure; 4. Data model design | High | Backend Platform | Completed | New models migrate cleanly and baseline lookup data is available in non-production and production. | Verified baseline migrations and seed_email_data command exist for demo mailboxes, templates, messages, routing decisions, and actions. | 2026-04-23
E-113 | Phase 1 | Shared Email Foundation | Provider Adapters | Define BaseEmailProviderAdapter contract | Implement the shared provider interface for mailbox subscription, polling, message fetch, attachment fetch, and outbound send. | Provider adapter base contract and tests | E-101, E-102 | 9. Provider integration design | Critical | Integration Engineering | Completed | All provider adapters follow one common contract and error model. | Verified BaseEmailProviderAdapter contract exists with subscribe, poll, get_message, get_attachments, and send_message methods. | 2026-04-23
E-114 | Phase 1 | Shared Email Foundation | Provider Adapters | Build Microsoft Graph provider adapter | Implement Microsoft Graph mailbox integration first, including subscription creation, message retrieval, attachment download, outbound send, and cursor handling. | Microsoft Graph adapter | E-113 | 9. Provider integration design | Critical | Integration Engineering | In Progress | Graph adapter supports inbound, outbound, sync state, and recovery patterns. | MicrosoftGraphEmailAdapter exists but still behaves as a scaffold. Real Graph API subscription, polling, and send flows remain to be completed. | 2026-04-23
E-115 | Phase 1 | Shared Email Foundation | Provider Adapters | Implement webhook subscription lifecycle | Add subscription creation, renewal, validation, and revoke flows for provider webhooks plus secure endpoint verification. | Webhook subscription management service | E-114 | 8. Shared ingestion pipeline; 9. Provider integration design | Critical | Integration Engineering | In Progress | Mailbox subscriptions can be created, renewed, and recovered safely. | Webhook ingest endpoint exists and validates tokens, but full subscription renewal/revoke lifecycle is not implemented yet. | 2026-04-23
E-116 | Phase 1 | Shared Email Foundation | Provider Adapters | Implement polling fallback | Add Celery-based mailbox polling for tenants or providers where webhooks are unavailable, delayed, or in recovery mode. | Polling implementation and scheduling strategy | E-113, E-114 | 9. Provider integration design; 10. Celery task architecture | High | Integration Engineering | In Progress | Polling can catch up missed messages and respects tenant mailboxes and backoff rules. | Polling fallback tasks and routing exist, but provider adapter polling is still stubbed for live mailbox retrieval. | 2026-04-23
E-117 | Phase 1 | Shared Email Foundation | Provider Adapters | Implement recovery and backfill sync | Support replay by cursor or date window to recover from downtime, token expiry, or missed webhooks. | Recovery and backfill sync service | E-114, E-116 | 9. Provider integration design | High | Integration Engineering | Not Started | Backfill can restore mailbox state without duplicate processing. | Backfill or recovery sync by cursor/date window has not been implemented in provider adapters yet. | 2026-04-23
E-118 | Phase 1 | Shared Email Foundation | Mailbox Services | Build MailboxService | Create mailbox registration, sync state management, health tracking, default route handling, provider auth metadata management, and activation or deactivation workflows. | MailboxService implementation | E-104, E-113 | 8. Shared ingestion pipeline; 9. Provider integration design | Critical | Backend Platform | Completed | MailboxService manages mailbox lifecycle, sync state, and safe activation. | Verified MailboxService handles adapter selection, mailbox resolution, sync, and test flows. | 2026-04-23
E-119 | Phase 1 | Shared Email Foundation | Inbound APIs | Implement inbound webhook endpoints | Create secure inbound webhook endpoints for Microsoft and Gmail style notification flows, including validation, authentication, and minimal intake logic. | Webhook receivers and request validation | E-115, E-118 | 16. API design | Critical | Backend API | Completed | Webhook endpoints accept valid provider events and reject malformed or unauthorized calls. | Verified webhook-facing views for inbound intake are implemented. | 2026-04-23
E-120 | Phase 1 | Shared Email Foundation | Ingestion | Build InboundIngestionService normalization | Normalize provider payloads into canonical thread, message, participant, and attachment metadata while preserving raw headers and provider payloads. | InboundIngestionService | E-105, E-106, E-107, E-108, E-113 | 8. Shared ingestion pipeline | Critical | Backend Platform | Completed | Provider-specific payloads are normalized to one canonical schema. | Verified InboundIngestionService normalization flow exists. | 2026-04-23
E-121 | Phase 1 | Shared Email Foundation | Ingestion | Implement idempotent deduplication | Deduplicate inbound messages by provider message ID, internet message ID, attachment hash, and replay window so retries and backfills remain safe. | Idempotent message ingest rules | E-120 | 8. Shared ingestion pipeline | Critical | Backend Platform | Completed | Repeated provider events do not create duplicate canonical records or duplicate downstream actions. | Verified provider message id uniqueness and ingest deduplication constraints are present in canonical model flow. | 2026-04-23
E-122 | Phase 1 | Shared Email Foundation | Attachment Processing | Build AttachmentService | Download, validate, hash, classify, and store email attachments, then link them to EmailAttachment and optionally to DocumentUpload. | AttachmentService | E-107, E-120 | 8. Shared ingestion pipeline | Critical | Backend Platform | Completed | Attachments are safely stored with hash and content metadata and linked back to their messages. | Verified AttachmentService exists for attachment persistence and linking. | 2026-04-23
E-123 | Phase 1 | Shared Email Foundation | Attachment Processing | Integrate attachment safety checks | Add virus or file safety scanning, content type allow lists, size limits, and blocked file handling before attachments can trigger business actions. | Attachment safety scanning workflow | E-122 | 15. Security, RBAC, and governance | Critical | Security Engineering | In Progress | Unsafe attachments are blocked, logged, and cannot trigger downstream automation. | Attachment processing metadata exists, but enterprise malware scanning integration still needs completion. | 2026-04-23
E-124 | Phase 1 | Shared Email Foundation | Canonical Persistence | Persist threads, messages, attachments, and participants | Finalize canonical storage creation logic and ensure provider events create complete thread, message, attachment, and participant records with traceability. | Canonical persistence flow | E-120, E-121, E-122 | 8. Shared ingestion pipeline | Critical | Backend Platform | Completed | Every accepted provider event is fully represented in canonical storage. | Verified canonical thread, message, participant, and attachment persistence flow exists. | 2026-04-23
E-125 | Phase 1 | Shared Email Foundation | Classification | Build deterministic ClassificationService | Implement rule-based classification using mailbox context, sender trust, subject keywords, body preview, attachment types, and entity references. | ClassificationService deterministic rules | E-103, E-124 | 6. Domain routing architecture; 8. Shared ingestion pipeline | Critical | Backend Platform | Completed | The first-pass classifier can deterministically classify common AP and procurement scenarios. | Verified deterministic classification and triage service implementation exists. | 2026-04-23
E-126 | Phase 1 | Shared Email Foundation | Classification | Add optional LLM fallback classification | Use a tightly bounded LLM assist path only when deterministic confidence is below threshold and keep final actions policy-checked. | LLM fallback classification path | E-125 | 6. Domain routing architecture; Appendix B. Recommended routing rules | High | AI Platform | Not Started | Ambiguous messages can be classified with bounded LLM assistance without bypassing policy checks. | LLM fallback classification path has not been wired yet; current flow is deterministic only. | 2026-04-23
E-127 | Phase 1 | Shared Email Foundation | Linking | Build ThreadLinkingService | Maintain conversation continuity, link replies to existing business threads, and update primary or last-message references on downstream entities. | ThreadLinkingService | E-105, E-106, E-124 | 8. Shared ingestion pipeline | Critical | Backend Platform | Completed | Replies can be linked to existing AP or procurement threads with deterministic confidence. | Verified ThreadLinkingService exists and relink task support is implemented. | 2026-04-23
E-128 | Phase 1 | Shared Email Foundation | Linking | Build EntityLinkingService | Resolve AP case, invoice, PO, procurement request, supplier quotation, or analysis run references from subject, body, sender, and thread context. | EntityLinkingService | E-124, E-127 | 8. Shared ingestion pipeline | Critical | Backend Platform | Completed | Entity linking supports both AP and procurement reference resolution patterns. | Verified EntityLinkingService exists for AP/procurement reference resolution. | 2026-04-23
E-129 | Phase 1 | Shared Email Foundation | Routing | Build deterministic-first EmailRoutingService | Implement ordered routing rules for explicit mailbox, thread continuation, attachment type, entity references, sender role, and optional LLM assist. | EmailRoutingService | E-125, E-127, E-128 | 6. Domain routing architecture; Appendix B. Recommended routing rules | Critical | Backend Platform | Completed | Routing rules execute in the documented order with confidence scoring and policy gates. | Verified deterministic-first RoutingService exists with domain handler dispatch and decision persistence. | 2026-04-23
E-130 | Phase 1 | Shared Email Foundation | Routing | Persist routing evidence and execution status | Store handler choice, confidence, deterministic flag, rule family, LLM usage, reasoning summary, and final status for every routing event. | Routing decision persistence flow | E-109, E-129 | 4. Data model design; 6. Domain routing architecture | Critical | Backend Platform | Completed | Every routed message has a complete evidence trail for audit, triage, and replay. | Verified routing evidence, rule metadata, confidence, and status are persisted in EmailRoutingDecision. | 2026-04-23
E-131 | Phase 1 | Shared Email Foundation | Triage | Implement ManualTriageHandler and triage queue | Create a manual triage path for messages that are unsafe, ambiguous, or unsupported, with role-based assignment and replay support. | Manual triage workflow | E-129, E-130 | 7. Domain handler architecture; 17. UI design | High | Operations Engineering | Completed | Ambiguous messages can be manually resolved and reprocessed safely. | Verified triage path and dashboard/workflow support exist for ambiguous messages. | 2026-04-23
E-132 | Phase 1 | Shared Email Foundation | Async Processing | Create email Celery queues and routing | Define email_ingestion, email_processing, email_outbound, and email_recovery queues and route tasks to the correct workers. | Queue configuration and task routing | E-102 | 10. Celery task architecture | High | Platform Operations | Completed | Email tasks are isolated by workload type and support scale-out. | Verified dedicated email task set exists for ingestion, processing, outbound, and recovery workflows. | 2026-04-23
E-133 | Phase 1 | Shared Email Foundation | Async Processing | Implement mailbox sync and ingest tasks | Create sync_mailbox_task and ingest_provider_message_task to fetch provider events and enqueue canonical processing. | Mailbox sync and ingest task implementations | E-118, E-119, E-132 | 10. Celery task architecture | High | Backend Platform | Completed | Inbound retrieval tasks can sync a mailbox and hand over provider messages for normalization. | Verified mailbox sync and provider-message ingest tasks already exist. | 2026-04-23
E-134 | Phase 1 | Shared Email Foundation | Async Processing | Implement processing, attachment, and routing tasks | Create process_email_message_task, download_email_attachment_task, and route_email_message_task to normalize, store attachments, classify, link, and route each message. | Core email processing tasks | E-120, E-122, E-129, E-132 | 10. Celery task architecture | Critical | Backend Platform | Completed | Core processing tasks run idempotently and push messages toward handled or triaged outcomes. | Verified processing, attachment download, and routing tasks already exist. | 2026-04-23
E-135 | Phase 1 | Shared Email Foundation | Async Processing | Implement relink, retry, and health tasks | Create relink_email_threads_task, retry_failed_email_actions_task, and mailbox_health_check_task for recovery and operational maintenance. | Recovery and health task implementations | E-127, E-132 | 10. Celery task architecture | High | Platform Operations | Completed | Support tasks can recover thread state, retry failures, and surface mailbox health issues. | Verified relink, retry-failed, and mailbox-health tasks already exist. | 2026-04-23
E-201 | Phase 2 | Domain Enablement | Shared Handler Framework | Implement BaseEmailDomainHandler and handler registry | Create the shared domain handler contract, registration pattern, and execution orchestration for AP, procurement, notification-only, and triage handlers. | Base domain handler framework | E-129 | 7. Domain handler architecture | Critical | Backend Platform | Not Started | Handlers implement a common contract and can be invoked deterministically by routing decisions.
E-202 | Phase 2 | Domain Enablement | AP Domain | Extend AP source channels and linkage fields | Add EMAIL source channel support and new linkage fields such as primary email thread, last email message, and source message on AP-side entities. | AP model and enum updates | E-103, E-201 | 11. Changes required in AP domain | Critical | AP Backend | Completed | AP entities can represent email-originated events and retain thread context. | Verified AP-side email linkage fields already exist on APCase and DocumentUpload uses source_message linkage. | 2026-04-23
E-203 | Phase 2 | Domain Enablement | AP Domain | Expose email artifacts in AP case context | Allow email messages and attachments to surface as AP case artifacts or evidence records in the domain model and retrieval services. | AP evidence and artifact linkage | E-202 | 11. Changes required in AP domain | High | AP Backend | Not Started | AP users can view email-originated evidence within case workflows.
E-204 | Phase 2 | Domain Enablement | AP Domain | Implement APEmailHandler for new invoice intake | Validate sender and attachment rules, create DocumentUpload from invoice attachments, set source channel to EMAIL, and trigger standard extraction and AP case flow. | APEmailHandler new invoice flow | E-201, E-202, E-122 | 7. Domain handler architecture; 11. Changes required in AP domain | Critical | AP Backend | In Progress | New invoice emails create uploads and continue through the normal AP processing path. | APEmailHandler exists, but it currently records governed actions only. Full AP-side DocumentUpload/case orchestration linkage still needs completion. | 2026-04-23
E-205 | Phase 2 | Domain Enablement | AP Domain | Implement APEmailHandler for existing case replies | Link reply threads to AP cases, store attachments as evidence or new uploads, and update case thread metadata for follow-up processing. | APEmailHandler case reply flow | E-201, E-202, E-203, E-127 | 7. Domain handler architecture; 11. Changes required in AP domain | High | AP Backend | Not Started | Existing case replies are attached to the correct AP case and preserve message continuity.
E-206 | Phase 2 | Domain Enablement | AP Domain | Trigger AP downstream reruns on new evidence | Invoke extraction, case orchestration, reconciliation reruns, or supervisor analysis when an inbound reply changes the AP evidence set. | AP downstream rerun hooks | E-204, E-205 | 7. Domain handler architecture; 11. Changes required in AP domain | High | AP Backend | Not Started | New AP evidence can automatically re-enter the existing processing pipeline under guardrails.
E-207 | Phase 2 | Domain Enablement | Procurement Domain | Extend procurement source and thread linkage fields | Add source_channel and primary_email_thread style linkage to SupplierQuotation, ProcurementRequest, and AnalysisRun trigger source values. | Procurement model and enum updates | E-103, E-201 | 12. Changes required in procurement domain | Critical | Procurement Backend | Completed | Procurement entities can represent email-originated quotations, replies, and analysis triggers. | Completed in this pass: added procurement email linkage fields on ProcurementRequest and SupplierQuotation plus AnalysisRun.trigger_source, serializer exposure, admin support, and migration 0023. | 2026-04-23
E-208 | Phase 2 | Domain Enablement | Procurement Domain | Implement ProcurementEmailHandler for quotation intake | Create DocumentUpload from supplier quotation attachments, create or link SupplierQuotation, optionally create or link ProcurementRequest, set source to EMAIL, and trigger quotation prefill. | ProcurementEmailHandler quotation intake flow | E-201, E-207, E-122 | 7. Domain handler architecture; 12. Changes required in procurement domain | Critical | Procurement Backend | In Progress | Quotation emails create the right procurement entities and start the prefill workflow. | ProcurementEmailHandler exists, but full SupplierQuotation/ProcurementRequest creation and linkage orchestration still needs completion. | 2026-04-23
E-209 | Phase 2 | Domain Enablement | Procurement Domain | Implement ProcurementEmailHandler for clarification replies | Link reply threads to SupplierQuotation or ProcurementRequest, store revised documents, update structured response context, and prepare downstream reruns. | ProcurementEmailHandler clarification reply flow | E-201, E-207, E-127, E-128 | 7. Domain handler architecture; 12. Changes required in procurement domain | High | Procurement Backend | Not Started | Clarification replies update the right procurement records and preserve thread history.
E-210 | Phase 2 | Domain Enablement | Procurement Domain | Trigger procurement downstream reruns | Connect email-triggered procurement events to quotation prefill, validation, recommendation, and benchmark reruns where appropriate. | Procurement downstream rerun hooks | E-208, E-209 | 12. Changes required in procurement domain | High | Procurement Backend | Not Started | New supplier evidence can re-enter validation and analysis workflows without manual rekeying.
E-211 | Phase 2 | Domain Enablement | Notification Handling | Implement NotificationOnlyHandler | Create a safe handler for informational emails that should be recorded and surfaced without mutating business state. | NotificationOnlyHandler | E-201 | 7. Domain handler architecture | Medium | Backend Platform | Not Started | Informational emails are preserved but do not trigger business mutations.
E-212 | Phase 2 | Domain Enablement | Routing to Handlers | Wire routing decisions to handler execution | Connect EmailRoutingService outcomes to the correct domain handler task flow, ensure idempotent execution, and record EmailAction results. | Handler execution orchestration | E-130, E-201, E-204, E-208, E-211 | 7. Domain handler architecture; 8. Shared ingestion pipeline | Critical | Backend Platform | Not Started | A routed message always reaches one governed handler path or triage.
E-213 | Phase 2 | Domain Enablement | End-to-End Validation | Validate AP invoice email flow | Test the full AP invoice email path from provider event through canonical storage, routing, DocumentUpload creation, extraction, case creation, reconciliation, and optional agent execution. | AP invoice email end-to-end test pack | E-204, E-206 | 18. End-to-end flow examples | High | QA + AP Team | Not Started | The AP invoice email flow completes with expected records, actions, and trace coverage.
E-214 | Phase 2 | Domain Enablement | End-to-End Validation | Validate procurement quotation email flow | Test the procurement quotation path from supplier email to canonical storage, routing, upload creation, SupplierQuotation linkage, prefill, and analysis entry. | Procurement quotation end-to-end test pack | E-208, E-210 | 18. End-to-end flow examples | High | QA + Procurement Team | Not Started | Quotation emails produce the right procurement records and downstream triggers.
E-215 | Phase 2 | Domain Enablement | End-to-End Validation | Validate procurement clarification reply flow | Test outbound clarification, supplier reply linking, revised attachment storage, response parsing, and rerun triggers for procurement workflows. | Procurement clarification reply end-to-end test pack | E-209, E-210 | 18. End-to-end flow examples | High | QA + Procurement Team | Not Started | Clarification replies remain on the same thread and update analysis inputs correctly.
E-301 | Phase 3 | Outbound Communication | Templates | Implement EmailTemplate management service | Build CRUD services and validation rules for outbound templates, variable substitution, approval requirements, and domain scoping. | EmailTemplate service layer | E-111 | 4. Data model design; 17. UI design | High | Backend Platform | Completed | Templates can be created, validated, versioned, and used safely by outbound flows. | Completed in this pass: strengthened EmailTemplate service behavior by validating required variables before send. | 2026-04-23
E-302 | Phase 3 | Outbound Communication | Outbound Engine | Build OutboundEmailService | Create the shared outbound sending service that uses templates, tracks delivery intent, writes EmailMessage and EmailAction, and supports audited sends. | OutboundEmailService | E-113, E-301 | 8. Shared ingestion pipeline; 9. Provider integration design | Critical | Backend Platform | Completed | Outbound sends are templated, audited, and provider-agnostic. | Completed in this pass: fixed outbound template rendering to support seeded template syntax and return rendered content for downstream persistence. | 2026-04-23
E-303 | Phase 3 | Outbound Communication | AP Outbound | Implement AP clarification send action | Provide AP-specific actions to send vendor clarification emails from a case or review context using approved templates and tracked threads. | AP clarification email action | E-302, E-202 | 13. Agent integration design; 17. UI design | High | AP Backend | Not Started | AP users can send governed clarification emails and keep them on a canonical thread.
E-304 | Phase 3 | Outbound Communication | Procurement Outbound | Implement procurement clarification send action | Provide procurement-specific outbound actions for supplier clarification requests, revision requests, and follow-up communication. | Procurement clarification email action | E-302, E-207 | 13. Agent integration design; 17. UI design | High | Procurement Backend | Not Started | Procurement users can send clarification emails tied to the correct quotation or request.
E-305 | Phase 3 | Outbound Communication | Notifications | Implement template-driven notification sends | Support notification emails for recommendation, benchmark, approval, or review outcomes with variable validation and audit logging. | Notification send workflows | E-302, E-301 | 7. Domain handler architecture; 17. UI design | Medium | Backend Platform | Not Started | System notifications can be sent with approved templates and full traceability.
E-306 | Phase 3 | Outbound Communication | Canonical Persistence | Persist outbound thread and message state | Ensure outbound messages are stored in the canonical EmailThread and EmailMessage model and can be correlated with replies and actions. | Outbound message persistence flow | E-302 | 4. Data model design; 8. Shared ingestion pipeline | High | Backend Platform | Not Started | Replies to outbound messages can be linked to the same canonical thread.
E-307 | Phase 3 | Outbound Communication | Async Processing | Implement outbound email tasks | Create send_templated_email_task and send_clarification_email_task with retry, failure capture, and trace propagation. | Outbound task implementations | E-302, E-132 | 10. Celery task architecture | High | Backend Platform | Completed | Outbound email tasks can send, retry, and record failures without losing trace context. | Verified outbound Celery tasks for templated send and clarification send already exist. | 2026-04-23
E-308 | Phase 3 | Outbound Communication | Provider Adapters | Validate provider send_message support | Complete outbound provider support and confirm each adapter can send messages with reply threading and delivery metadata capture. | Provider outbound send validation | E-302, E-306 | 9. Provider integration design | High | Integration Engineering | In Progress | The active provider adapter fully supports outbound sending and thread continuity. | Provider send_message hooks exist, but Microsoft Graph and Gmail live outbound delivery remains scaffold-level. | 2026-04-23
E-401 | Phase 4 | Governed Automation | RBAC | Implement shared email permission set | Add platform email permissions and domain-specific email capabilities to the RBAC model and default role matrix. | Email permission catalog and role assignments | E-002, E-101 | 15. Security, RBAC, and governance | Critical | Security + RBAC | Completed | Permissions cover view, thread read, attachment read, send, manage mailboxes, route, triage, and domain-specific actions. | Verified email RBAC permissions are seeded in migration 0002 and enforced in API and UI layers. | 2026-04-23
E-402 | Phase 4 | Governed Automation | Shared Tools | Implement shared email tools | Create governed tools for email_thread_lookup, email_attachment_list, email_body_summary, match_email_to_entity, send_templated_email, and extract_email_intent. | Shared email toolset | E-401, E-302 | 13. Agent integration design | High | Agent Platform | Completed | Shared tools enforce tenant scope, permission checks, and safe outputs. | Verified shared email tools exist for thread lookup, attachment list, body summary, entity match, templated send, and intent extraction. | 2026-04-23
E-403 | Phase 4 | Governed Automation | AP Tools | Implement AP email tool wrappers | Create AP-safe wrappers such as attach_email_to_case, extract_case_approval_from_email, and send_vendor_clarification_email. | AP email wrapper tools | E-402, E-204, E-303 | 13. Agent integration design | High | Agent Platform + AP | Completed | AP wrappers expose only policy-approved actions and use existing AP services. | Verified AP-specific wrapper tools exist for case attachment, approval extraction, and vendor clarification send. | 2026-04-23
E-404 | Phase 4 | Governed Automation | Procurement Tools | Implement procurement email tool wrappers | Create wrappers for attaching email to procurement requests or supplier quotations, extracting supplier response fields, and sending supplier clarification emails. | Procurement email wrapper tools | E-402, E-208, E-304 | 13. Agent integration design | High | Agent Platform + Procurement | Completed | Procurement wrappers invoke procurement services without forcing AP agent model convergence. | Verified procurement-specific wrapper tools exist for procurement request/quotation attachment, supplier response extraction, and supplier clarification send. | 2026-04-23
E-405 | Phase 4 | Governed Automation | AP Agent Integration | Integrate email tools with SupervisorAgent and AP agents | Expose the governed email capabilities to AP-side agents under existing guardrails and recommendation policies. | AP agent email integration | E-403 | 13. Agent integration design | High | Agent Platform + AP | Not Started | AP agents can access email context through scoped tools only.
E-406 | Phase 4 | Governed Automation | Procurement Agent Integration | Bridge procurement wrappers into procurement orchestration | Connect procurement email tools to procurement services, AnalysisRun, and ProcurementAgentOrchestrator style flows without collapsing execution models. | Procurement orchestration bridge | E-404 | 13. Agent integration design; 20. Recommended target-state decisions | High | Agent Platform + Procurement | Not Started | Procurement automation stays aligned to procurement execution models after routing.
E-407 | Phase 4 | Governed Automation | System Services | Implement shared system email services or agents | Create SYSTEM_EMAIL_INTAKE, SYSTEM_EMAIL_ROUTER, SYSTEM_EMAIL_THREAD_LINKER, and SYSTEM_NOTIFICATION_DISPATCH as deterministic services or system agents. | Shared system email services | E-134, E-135, E-401 | 14. System agent design | High | Platform Architecture | Not Started | Shared system components can process, route, and dispatch notifications under service identity.
E-408 | Phase 4 | Governed Automation | System Services | Implement SYSTEM_AP_EMAIL_HANDLER adapter | Provide the AP-facing system adapter that aligns with the existing system-agent model while calling AP services safely. | AP system email handler | E-204, E-407 | 14. System agent design | Medium | AP Backend | Not Started | AP system handler can execute deterministic AP email workflows without bypassing existing guardrails.
E-409 | Phase 4 | Governed Automation | System Services | Implement SYSTEM_PROCUREMENT_EMAIL_HANDLER adapter | Provide the procurement-facing system adapter that terminates into procurement services and orchestration rather than AP case handling. | Procurement system email handler | E-208, E-407 | 14. System agent design | Medium | Procurement Backend | Not Started | Procurement system handler invokes procurement services while preserving procurement-side execution records.
E-410 | Phase 4 | Governed Automation | Governance | Audit and trace all agent-safe email actions | Ensure all email tool calls, system service actions, and automation decisions write EmailAction, AuditEvent, ProcessingLog, and trace context. | Governed automation audit trail | E-402, E-403, E-404, E-407 | 15. Security, RBAC, and governance | Critical | Platform Governance | Not Started | Every automated email action is fully attributable and replayable.
E-501 | Phase 5 | Advanced Capabilities | Approval by Email | Implement approval-by-email tokens and validation | Build tokenized or validated action codes for approval-by-email while blocking unsafe actions from unknown senders. | Approval-by-email workflow | E-302, E-401 | 15. Security, RBAC, and governance; 19. Recommended implementation phases | Medium | Security + AP | Not Started | Approval-by-email requires trusted sender validation, token checks, and full audit coverage.
E-502 | Phase 5 | Advanced Capabilities | Trust and Safety | Implement sender trust scoring and unknown-sender controls | Operationalize trust scoring, blocked auto-approval, sender allow or deny logic, and suspicious message handling across all message types. | Sender trust scoring engine | E-125, E-401 | 5. Important enum design; 15. Security, RBAC, and governance | High | Security Engineering | Not Started | Unknown or suspicious senders cannot trigger high-risk automation paths.
E-503 | Phase 5 | Advanced Capabilities | Analytics | Implement email analytics and SLA monitoring | Create operational metrics for mailbox health, processing latency, routing outcomes, triage volume, outbound delivery, and domain throughput. | Email analytics and SLA dashboard data | E-005, E-135, E-410 | 15. Security, RBAC, and governance; 19. Recommended implementation phases | Medium | Platform Analytics | Not Started | Operations can track SLA performance and bottlenecks across mailboxes and handlers.
E-504 | Phase 5 | Advanced Capabilities | Intelligence | Implement suggested replies and summarization | Add bounded summarization and suggested reply generation for triage, AP, and procurement users using safe, auditable prompts. | Suggested reply and summary capability | E-302, E-402 | 19. Recommended implementation phases | Medium | AI Platform | Not Started | Generated summaries and suggestions are traceable, reviewed, and cannot bypass permission rules.
E-505 | Phase 5 | Advanced Capabilities | Automation | Implement auto-reopen logic based on reply content | Detect business-relevant replies that should reopen AP or procurement work items and define guardrails for when this can happen automatically. | Auto-reopen decision workflow | E-205, E-209, E-502 | 19. Recommended implementation phases | Medium | AP + Procurement | Not Started | Relevant replies can reopen work safely with traceable decision logic.
E-506 | Phase 5 | Advanced Capabilities | Operations | Implement triage insights and operational dashboards | Provide dashboards for failed actions, aging triage items, mailbox health, routing confidence distribution, and handler workload. | Operational dashboard feature set | E-503 | 17. UI design; 19. Recommended implementation phases | Medium | Operations Engineering | Not Started | Support teams can triage failures and workload from one operational view.
E-601 | Cross-Cutting | Security and Governance | Security Controls | Enforce tenant-scoped credentials and configured mailbox boundaries | Prevent cross-tenant mailbox access, require tenant-scoped credential storage, and allow processing only for approved mailboxes. | Tenant-safe credential and mailbox enforcement | E-104, E-118, E-401 | 15. Security, RBAC, and governance | Critical | Security Engineering | Not Started | Only approved tenant mailboxes can be activated and used by the platform.
E-602 | Cross-Cutting | Security and Governance | Traceability | Propagate trace IDs and span IDs end to end | Ensure trace context flows across webhook intake, Celery tasks, routing, handler execution, outbound sends, and downstream AP or procurement processing. | End-to-end trace propagation | E-134, E-212, E-307 | 15. Security, RBAC, and governance | Critical | Platform Observability | Not Started | One email can be traced across all ingestion, routing, domain, and outbound steps.
E-603 | Cross-Cutting | Security and Governance | Audit Logging | Standardize EmailAction, AuditEvent, and ProcessingLog writes | Guarantee that every email-triggered mutation writes the correct action, audit, and processing records with consistent payload summaries and result states. | Standardized email audit instrumentation | E-110, E-130, E-212 | 15. Security, RBAC, and governance | Critical | Platform Governance | Not Started | Audit records are complete, queryable, and consistent across all handler paths.
E-604 | Cross-Cutting | API Delivery | Mailbox Administration APIs | Build mailbox admin endpoints | Deliver mailbox configuration endpoints with create, read, update, test, sync, activation, and deactivation capabilities. | Mailbox admin API endpoints | E-104, E-118 | 16. API design | High | Backend API | Completed | Admins can manage mailboxes entirely through governed APIs. | Verified mailbox admin API endpoints exist with list/create/update plus sync/test actions. | 2026-04-23
E-605 | Cross-Cutting | API Delivery | Email Operations APIs | Build email operations endpoints | Deliver endpoints to list messages, read threads, route a message, and reprocess a message with status and evidence visibility. | Email operations API endpoints | E-106, E-109, E-129 | 16. API design | High | Backend API | Completed | Operators can inspect and reprocess email records through secure APIs. | Verified email operations API endpoints exist for messages, threads, routing decisions, actions, and reprocess/route operations. | 2026-04-23
E-606 | Cross-Cutting | API Delivery | Entity Linking APIs | Build linking endpoints | Create APIs to link messages to AP cases, procurement requests, or supplier quotations and to correct routing when manual intervention is needed. | Email linking API endpoints | E-127, E-128, E-131 | 16. API design | High | Backend API | Completed | Manual linking and reclassification can be performed through governed endpoints. | Verified message link-entity API endpoint exists for manual AP/procurement linkage. | 2026-04-23
E-607 | Cross-Cutting | API Delivery | Outbound APIs | Build outbound send endpoints | Deliver APIs for sending templates, clarification requests, and notifications while enforcing permissions and audit logging. | Outbound email API endpoints | E-302, E-303, E-304, E-305 | 16. API design | High | Backend API | In Progress | Outbound actions are available via secure APIs and align with service rules. | Template CRUD is exposed by API, but dedicated outbound send endpoints still need to be added to match the task definition fully. | 2026-04-23
E-608 | Cross-Cutting | UI Delivery | Platform UI | Build mailbox configuration UI | Create platform pages for mailbox setup, status, provider health, sync testing, and activation controls. | Mailbox configuration screens | E-604 | 17. UI design | Medium | Frontend + Backend | Completed | Admins can configure mailboxes and inspect sync state from the platform UI. | Verified dashboard includes mailbox configuration workflow. | 2026-04-23
E-609 | Cross-Cutting | UI Delivery | Platform UI | Build inbox, triage, and failed action dashboards | Provide platform pages for processing dashboards, triage queue, failed actions, and email health visibility. | Platform email operations screens | E-605, E-131, E-506 | 17. UI design | Medium | Frontend + Backend | Completed | Operators can work failed and triaged emails from one workspace. | Verified dashboard includes inbox, triage, failed action, and mailbox health sections. | 2026-04-23
E-610 | Cross-Cutting | UI Delivery | AP UI | Build AP case email timeline and thread panel | Add AP UI components for email timeline, linked thread view, related attachments, and vendor clarification actions. | AP email timeline UI | E-203, E-303 | 17. UI design | Medium | AP Frontend | Not Started | AP users can see email history and act from the case context.
E-611 | Cross-Cutting | UI Delivery | Procurement UI | Build procurement email timeline and supplier thread panels | Add procurement UI components for request-level email timeline, supplier quotation thread view, clarification history, and outbound actions. | Procurement email timeline UI | E-209, E-304 | 17. UI design | Medium | Procurement Frontend | Not Started | Procurement users can review inbound and outbound supplier communication in context.
E-612 | Cross-Cutting | Quality Engineering | Unit and Integration Tests | Create unit and integration tests for core email services | Cover models, provider adapters, ingestion, attachment safety, classification, linking, routing, handlers, APIs, and permissions. | Automated unit and integration test suite | E-135, E-212, E-607 | 18. End-to-end flow examples | Critical | QA Automation | Not Started | Core email services are covered with deterministic tests and regression protection. | No dedicated automated test suite exists yet for apps.email_integration. Validation so far is implementation review and manual verification. | 2026-04-23
E-613 | Cross-Cutting | Quality Engineering | Security Testing | Run trust, RBAC, and tenant-isolation tests | Validate permission boundaries, tenant scoping, unknown sender controls, attachment safety behavior, and approval token misuse handling. | Security and tenancy test pack | E-401, E-501, E-601 | 15. Security, RBAC, and governance | Critical | Security QA | Not Started | Security tests prove that risky email actions are blocked or scoped correctly.
E-614 | Cross-Cutting | Quality Engineering | Performance and Resilience | Run load, retry, and failure-mode tests | Test mailbox bursts, large attachments, retry behavior, webhook replay, polling fallback, and recovery sync under operational load. | Performance and resilience test report | E-116, E-117, E-135 | 8. Shared ingestion pipeline; 9. Provider integration design | High | Performance Engineering | Not Started | The platform stays stable under burst load and recovers cleanly from provider or worker failures.
E-615 | Cross-Cutting | Operational Readiness | Runbooks and Support | Create runbooks, operational docs, and handover material | Document mailbox onboarding, provider auth renewal, replay or backfill, failed action handling, triage, and support escalation. | Operations and support runbook set | E-007, E-506 | 17. UI design; 19. Recommended implementation phases | Medium | Platform Operations | Not Started | Support teams can onboard, troubleshoot, and recover email processing without code changes.
E-616 | Cross-Cutting | Operational Readiness | Release Management | Define production rollout and hypercare plan | Prepare pilot release, phased enablement, monitoring thresholds, rollback steps, and post-go-live hypercare ownership. | Production rollout and hypercare plan | E-003, E-615 | 19. Recommended implementation phases | Medium | Program Management | Not Started | Go-live plan includes rollback, monitoring, ownership, and success review checkpoints.

## Overview
Detailed Email Target Architecture - Task Breakdown Overview
Source document | detailed_email_target_architecture.docx |  | Tracker status | Count
Extracted text source | detailed_email_target_architecture_extracted.txt |  | Completed | 43
Generated workbook | detailed_email_target_architecture_task_breakdown.xlsx |  | In Progress | 8
Generated on | 2026-04-23 07:12:10 |  | Not Started | 46
Total tasks | 97 |  | Last review | 2026-04-23 07:23:28
Architecture summary
A shared, tenant-scoped email integration layer ingests, normalizes, classifies, links, and routes inbound and outbound email activity into AP and procurement workflows while preserving domain-specific orchestration, RBAC, audit, and async execution models.
Phase | Goal | Task Count
Phase 0 | Planning, scope confirmation, target-state alignment, and delivery sequencing. | 7
Phase 1 | Shared inbound email foundation: app, models, provider integration, ingestion, classification, routing, and triage. | 35
Phase 2 | AP and procurement domain handlers plus thread/entity linkage and downstream orchestration hooks. | 15
Phase 3 | Outbound email communication, templates, clarification workflows, and notifications. | 8
Phase 4 | Agent-safe tools, system handlers, and governed automation surfaces. | 10
Phase 5 | Advanced actions, analytics, approval-by-email, and operational intelligence. | 6
Cross-Cutting | Security, governance, API/UI delivery, testing, observability, readiness, and rollout support. | 16
Milestone | Definition
M1 | Shared foundation ready - Mailbox config, canonical models, provider integration, ingestion, classification, routing, triage, and core async tasks are complete.
M2 | Domain handlers live - AP and procurement inbound flows are functional end to end with thread and entity linking.
M3 | Outbound enabled - Templates, outbound service, clarification sends, notifications, and reply threading are complete.
M4 | Governed automation enabled - Email permissions, tools, system handlers, and audit instrumentation are active.
M5 | Advanced operations ready - Approval-by-email, analytics, dashboards, and production runbooks are delivered.

## Section Coverage
Document Section | Coverage Goal | Related Task IDs | Related Task Names
1. Architecture goal | Define shared email capability scope and platform handoff boundaries. | E-001 | Validate scope and success criteria
2. Target high-level architecture | Confirm shared email app and domain-specific downstream execution paths. | E-102 | Register app configuration and extension points
3. New app structure | Create app structure, services, handlers, tools, tasks, and migrations. | E-101, E-102, E-112 | Create apps.email_integration structure ¦ Register app configuration and extension points ¦ Create migrations and seed baseline records
4. Data model design | Implement mailbox, thread, message, attachment, participant, routing, action, and template entities. | E-104, E-105, E-106, E-107, E-108, E-109, E-110, E-111, E-112, E-130, E-301, E-306 | Implement MailboxConfig model ¦ Implement EmailThread model ¦ Implement EmailMessage model ¦ Implement EmailAttachment model ¦ Implement EmailParticipant model ¦ Implement EmailRoutingDecision model ¦ Implement EmailAction model ¦ Implement EmailTemplate model ¦ Create migrations and seed baseline records ¦ Persist routing evidence and execution status ¦ Implement EmailTemplate management service ¦ Persist outbound thread and message state
5. Important enum design | Add canonical email enums for classification, processing, trust, intent, and actions. | E-103, E-502 | Add canonical email enums ¦ Implement sender trust scoring and unknown-sender controls
6. Domain routing architecture | Build deterministic-first routing with rule groups and optional LLM fallback. | E-109, E-125, E-126, E-129, E-130 | Implement EmailRoutingDecision model ¦ Build deterministic ClassificationService ¦ Add optional LLM fallback classification ¦ Build deterministic-first EmailRoutingService ¦ Persist routing evidence and execution status
7. Domain handler architecture | Create AP, procurement, notification, and manual triage handlers. | E-131, E-201, E-204, E-205, E-206, E-208, E-209, E-211, E-212, E-305 | Implement ManualTriageHandler and triage queue ¦ Implement BaseEmailDomainHandler and handler registry ¦ Implement APEmailHandler for new invoice intake ¦ Implement APEmailHandler for existing case replies ¦ Trigger AP downstream reruns on new evidence ¦ Implement ProcurementEmailHandler for quotation intake ¦ Implement ProcurementEmailHandler for clarification replies ¦ Implement NotificationOnlyHandler ¦ Wire routing decisions to handler execution ¦ Implement template-driven notification sends
8. Shared ingestion pipeline | Implement provider fetch, normalization, attachment handling, linking, routing, and audit trail. | E-115, E-118, E-120, E-121, E-122, E-124, E-125, E-127, E-128, E-212, E-302, E-306, E-614 | Implement webhook subscription lifecycle ¦ Build MailboxService ¦ Build InboundIngestionService normalization ¦ Implement idempotent deduplication ¦ Build AttachmentService ¦ Persist threads, messages, attachments, and participants ¦ Build deterministic ClassificationService ¦ Build ThreadLinkingService ¦ Build EntityLinkingService ¦ Wire routing decisions to handler execution ¦ Build OutboundEmailService ¦ Persist outbound thread and message state ¦ Run load, retry, and failure-mode tests
9. Provider integration design | Build Microsoft Graph first, Gmail second, with webhook, polling, and recovery sync. | E-004, E-007, E-113, E-114, E-115, E-116, E-117, E-118, E-302, E-308, E-614 | Define mailbox rollout strategy ¦ Define cutover and backfill approach ¦ Define BaseEmailProviderAdapter contract ¦ Build Microsoft Graph provider adapter ¦ Implement webhook subscription lifecycle ¦ Implement polling fallback ¦ Implement recovery and backfill sync ¦ Build MailboxService ¦ Build OutboundEmailService ¦ Validate provider send_message support ¦ Run load, retry, and failure-mode tests
10. Celery task architecture | Create async tasks and dedicated email queues. | E-116, E-132, E-133, E-134, E-135, E-307 | Implement polling fallback ¦ Create email Celery queues and routing ¦ Implement mailbox sync and ingest tasks ¦ Implement processing, attachment, and routing tasks ¦ Implement relink, retry, and health tasks ¦ Implement outbound email tasks
11. Changes required in AP domain | Add email source channels, case/message links, and reuse AP processing flows. | E-202, E-203, E-204, E-205, E-206 | Extend AP source channels and linkage fields ¦ Expose email artifacts in AP case context ¦ Implement APEmailHandler for new invoice intake ¦ Implement APEmailHandler for existing case replies ¦ Trigger AP downstream reruns on new evidence
12. Changes required in procurement domain | Add email linkage and rerun hooks for quotation and request flows. | E-207, E-208, E-209, E-210 | Extend procurement source and thread linkage fields ¦ Implement ProcurementEmailHandler for quotation intake ¦ Implement ProcurementEmailHandler for clarification replies ¦ Trigger procurement downstream reruns
13. Agent integration design | Expose governed email tools and wrappers rather than raw mailbox access. | E-303, E-304, E-402, E-403, E-404, E-405, E-406 | Implement AP clarification send action ¦ Implement procurement clarification send action ¦ Implement shared email tools ¦ Implement AP email tool wrappers ¦ Implement procurement email tool wrappers ¦ Integrate email tools with SupervisorAgent and AP agents ¦ Bridge procurement wrappers into procurement orchestration
14. System agent design | Provide shared and domain system agents or deterministic services. | E-407, E-408, E-409 | Implement shared system email services or agents ¦ Implement SYSTEM_AP_EMAIL_HANDLER adapter ¦ Implement SYSTEM_PROCUREMENT_EMAIL_HANDLER adapter
15. Security, RBAC, and governance | Enforce permissions, trust, safety checks, and full trace/audit coverage. | E-005, E-006, E-110, E-123, E-401, E-410, E-501, E-502, E-503, E-601, E-602, E-603, E-613 | Define SLAs and operational guardrails ¦ Define tenant, retention, and data residency approach ¦ Implement EmailAction model ¦ Integrate attachment safety checks ¦ Implement shared email permission set ¦ Audit and trace all agent-safe email actions ¦ Implement approval-by-email tokens and validation ¦ Implement sender trust scoring and unknown-sender controls ¦ Implement email analytics and SLA monitoring ¦ Enforce tenant-scoped credentials and configured mailbox boundaries ¦ Propagate trace IDs and span IDs end to end ¦ Standardize EmailAction, AuditEvent, and ProcessingLog writes ¦ Run trust, RBAC, and tenant-isolation tests
16. API design | Deliver mailbox admin, email operations, linking, outbound, and webhook APIs. | E-119, E-604, E-605, E-606, E-607 | Implement inbound webhook endpoints ¦ Build mailbox admin endpoints ¦ Build email operations endpoints ¦ Build linking endpoints ¦ Build outbound send endpoints
17. UI design | Add platform, AP, and procurement email dashboards and workflow panels. | E-111, E-131, E-301, E-303, E-304, E-305, E-506, E-608, E-609, E-610, E-611, E-615 | Implement EmailTemplate model ¦ Implement ManualTriageHandler and triage queue ¦ Implement EmailTemplate management service ¦ Implement AP clarification send action ¦ Implement procurement clarification send action ¦ Implement template-driven notification sends ¦ Implement triage insights and operational dashboards ¦ Build mailbox configuration UI ¦ Build inbox, triage, and failed action dashboards ¦ Build AP case email timeline and thread panel ¦ Build procurement email timeline and supplier thread panels ¦ Create runbooks, operational docs, and handover material
18. End-to-end flow examples | Validate AP invoice, procurement quotation, and procurement clarification flows. | E-213, E-214, E-215, E-612 | Validate AP invoice email flow ¦ Validate procurement quotation email flow ¦ Validate procurement clarification reply flow ¦ Create unit and integration tests for core email services
19. Recommended implementation phases | Sequence delivery by foundation, handlers, outbound, tools, and advanced actions. | E-003, E-005, E-007, E-501, E-503, E-504, E-505, E-506, E-615, E-616 | Create implementation roadmap and sprint plan ¦ Define SLAs and operational guardrails ¦ Define cutover and backfill approach ¦ Implement approval-by-email tokens and validation ¦ Implement email analytics and SLA monitoring ¦ Implement suggested replies and summarization ¦ Implement auto-reopen logic based on reply content ¦ Implement triage insights and operational dashboards ¦ Create runbooks, operational docs, and handover material ¦ Define production rollout and hypercare plan
20. Recommended target-state decisions | Capture and confirm architecture decisions before implementation. | E-002, E-406 | Confirm target-state architecture decisions ¦ Bridge procurement wrappers into procurement orchestration
21. Final architecture summary | Keep email integration shared while preserving existing domain orchestration models. | E-001 | Validate scope and success criteria
Appendix A. Target component map | Map layers, responsibilities, and downstream targets.
Appendix B. Recommended routing rules | Trace routing rules by priority and expected outcomes. | E-126, E-129 | Add optional LLM fallback classification ¦ Build deterministic-first EmailRoutingService
Appendix C. Source alignment notes | Ensure the design stays aligned to the current AP and procurement platform model.

## Phase Plan
Phase | Goal | Representative Task IDs
Phase 0 | Planning, scope confirmation, target-state alignment, and delivery sequencing. | E-001, E-002, E-003, E-004, E-005, E-006, E-007
Phase 1 | Shared inbound email foundation: app, models, provider integration, ingestion, classification, routing, and triage. | E-101, E-102, E-103, E-104, E-105, E-106, E-107, E-108, E-109, E-110, E-111, E-112, E-113, E-114, E-115, E-116, E-117, E-118, E-119, E-120, E-121, E-122, E-123, E-124, E-125, E-126, E-127, E-128, E-129, E-130, E-131, E-132, E-133, E-134, E-135
Phase 2 | AP and procurement domain handlers plus thread/entity linkage and downstream orchestration hooks. | E-201, E-202, E-203, E-204, E-205, E-206, E-207, E-208, E-209, E-210, E-211, E-212, E-213, E-214, E-215
Phase 3 | Outbound email communication, templates, clarification workflows, and notifications. | E-301, E-302, E-303, E-304, E-305, E-306, E-307, E-308
Phase 4 | Agent-safe tools, system handlers, and governed automation surfaces. | E-401, E-402, E-403, E-404, E-405, E-406, E-407, E-408, E-409, E-410
Phase 5 | Advanced actions, analytics, approval-by-email, and operational intelligence. | E-501, E-502, E-503, E-504, E-505, E-506
Cross-Cutting | Security, governance, API/UI delivery, testing, observability, readiness, and rollout support. | E-601, E-602, E-603, E-604, E-605, E-606, E-607, E-608, E-609, E-610, E-611, E-612, E-613, E-614, E-615, E-616

## Decisions
Decision ID | Decision | Why it matters
D-1 | Use one shared apps.email_integration app for all email | Reduces duplication and centralizes mailbox, thread, routing, and governance capabilities.
D-2 | Use AP and procurement domain handlers instead of a generic business processor | Preserves each domain's business logic and downstream orchestration model.
D-3 | Keep DocumentUpload as the common attachment ingestion backbone | Reuses the existing ingestion anchor already shared by both domains.
D-4 | Use deterministic routing first and LLM assist only when confidence is low | Keeps routing predictable, auditable, and policy-driven.
D-5 | Do not give agents unrestricted mailbox access; use scoped and permissioned tools | Protects tenant email content and keeps automation within explicit guardrails.
D-6 | Keep AP and procurement execution models separate after routing | Avoids forcing procurement execution into AP case orchestration and maintains current architecture alignment.

## Dependencies
Task ID | Task Name | Depends On
E-001 | Validate scope and success criteria | None
E-002 | Confirm target-state architecture decisions | E-001
E-003 | Create implementation roadmap and sprint plan | E-001, E-002
E-004 | Define mailbox rollout strategy | E-002
E-005 | Define SLAs and operational guardrails | E-001
E-006 | Define tenant, retention, and data residency approach | E-001
E-007 | Define cutover and backfill approach | E-003, E-004
E-101 | Create apps.email_integration structure | E-002
E-102 | Register app configuration and extension points | E-101
E-103 | Add canonical email enums | E-101
E-104 | Implement MailboxConfig model | E-103
E-105 | Implement EmailThread model | E-103
E-106 | Implement EmailMessage model | E-103
E-107 | Implement EmailAttachment model | E-103
E-108 | Implement EmailParticipant model | E-103
E-109 | Implement EmailRoutingDecision model | E-103
E-110 | Implement EmailAction model | E-103
E-111 | Implement EmailTemplate model | E-103
E-112 | Create migrations and seed baseline records | E-104, E-105, E-106, E-107, E-108, E-109, E-110, E-111
E-113 | Define BaseEmailProviderAdapter contract | E-101, E-102
E-114 | Build Microsoft Graph provider adapter | E-113
E-115 | Implement webhook subscription lifecycle | E-114
E-116 | Implement polling fallback | E-113, E-114
E-117 | Implement recovery and backfill sync | E-114, E-116
E-118 | Build MailboxService | E-104, E-113
E-119 | Implement inbound webhook endpoints | E-115, E-118
E-120 | Build InboundIngestionService normalization | E-105, E-106, E-107, E-108, E-113
E-121 | Implement idempotent deduplication | E-120
E-122 | Build AttachmentService | E-107, E-120
E-123 | Integrate attachment safety checks | E-122
E-124 | Persist threads, messages, attachments, and participants | E-120, E-121, E-122
E-125 | Build deterministic ClassificationService | E-103, E-124
E-126 | Add optional LLM fallback classification | E-125
E-127 | Build ThreadLinkingService | E-105, E-106, E-124
E-128 | Build EntityLinkingService | E-124, E-127
E-129 | Build deterministic-first EmailRoutingService | E-125, E-127, E-128
E-130 | Persist routing evidence and execution status | E-109, E-129
E-131 | Implement ManualTriageHandler and triage queue | E-129, E-130
E-132 | Create email Celery queues and routing | E-102
E-133 | Implement mailbox sync and ingest tasks | E-118, E-119, E-132
E-134 | Implement processing, attachment, and routing tasks | E-120, E-122, E-129, E-132
E-135 | Implement relink, retry, and health tasks | E-127, E-132
E-201 | Implement BaseEmailDomainHandler and handler registry | E-129
E-202 | Extend AP source channels and linkage fields | E-103, E-201
E-203 | Expose email artifacts in AP case context | E-202
E-204 | Implement APEmailHandler for new invoice intake | E-201, E-202, E-122
E-205 | Implement APEmailHandler for existing case replies | E-201, E-202, E-203, E-127
E-206 | Trigger AP downstream reruns on new evidence | E-204, E-205
E-207 | Extend procurement source and thread linkage fields | E-103, E-201
E-208 | Implement ProcurementEmailHandler for quotation intake | E-201, E-207, E-122
E-209 | Implement ProcurementEmailHandler for clarification replies | E-201, E-207, E-127, E-128
E-210 | Trigger procurement downstream reruns | E-208, E-209
E-211 | Implement NotificationOnlyHandler | E-201
E-212 | Wire routing decisions to handler execution | E-130, E-201, E-204, E-208, E-211
E-213 | Validate AP invoice email flow | E-204, E-206
E-214 | Validate procurement quotation email flow | E-208, E-210
E-215 | Validate procurement clarification reply flow | E-209, E-210
E-301 | Implement EmailTemplate management service | E-111
E-302 | Build OutboundEmailService | E-113, E-301
E-303 | Implement AP clarification send action | E-302, E-202
E-304 | Implement procurement clarification send action | E-302, E-207
E-305 | Implement template-driven notification sends | E-302, E-301
E-306 | Persist outbound thread and message state | E-302
E-307 | Implement outbound email tasks | E-302, E-132
E-308 | Validate provider send_message support | E-302, E-306
E-401 | Implement shared email permission set | E-002, E-101
E-402 | Implement shared email tools | E-401, E-302
E-403 | Implement AP email tool wrappers | E-402, E-204, E-303
E-404 | Implement procurement email tool wrappers | E-402, E-208, E-304
E-405 | Integrate email tools with SupervisorAgent and AP agents | E-403
E-406 | Bridge procurement wrappers into procurement orchestration | E-404
E-407 | Implement shared system email services or agents | E-134, E-135, E-401
E-408 | Implement SYSTEM_AP_EMAIL_HANDLER adapter | E-204, E-407
E-409 | Implement SYSTEM_PROCUREMENT_EMAIL_HANDLER adapter | E-208, E-407
E-410 | Audit and trace all agent-safe email actions | E-402, E-403, E-404, E-407
E-501 | Implement approval-by-email tokens and validation | E-302, E-401
E-502 | Implement sender trust scoring and unknown-sender controls | E-125, E-401
E-503 | Implement email analytics and SLA monitoring | E-005, E-135, E-410
E-504 | Implement suggested replies and summarization | E-302, E-402
E-505 | Implement auto-reopen logic based on reply content | E-205, E-209, E-502
E-506 | Implement triage insights and operational dashboards | E-503
E-601 | Enforce tenant-scoped credentials and configured mailbox boundaries | E-104, E-118, E-401
E-602 | Propagate trace IDs and span IDs end to end | E-134, E-212, E-307
E-603 | Standardize EmailAction, AuditEvent, and ProcessingLog writes | E-110, E-130, E-212
E-604 | Build mailbox admin endpoints | E-104, E-118
E-605 | Build email operations endpoints | E-106, E-109, E-129
E-606 | Build linking endpoints | E-127, E-128, E-131
E-607 | Build outbound send endpoints | E-302, E-303, E-304, E-305
E-608 | Build mailbox configuration UI | E-604
E-609 | Build inbox, triage, and failed action dashboards | E-605, E-131, E-506
E-610 | Build AP case email timeline and thread panel | E-203, E-303
E-611 | Build procurement email timeline and supplier thread panels | E-209, E-304
E-612 | Create unit and integration tests for core email services | E-135, E-212, E-607
E-613 | Run trust, RBAC, and tenant-isolation tests | E-401, E-501, E-601
E-614 | Run load, retry, and failure-mode tests | E-116, E-117, E-135
E-615 | Create runbooks, operational docs, and handover material | E-007, E-506
E-616 | Define production rollout and hypercare plan | E-003, E-615